## AGILE - Product Backlog
Ben Kong and Sean Cornish | [5 empty] | For help use these links:
Superfighters Game | [5 empty] | https://www.mountaingoatsoftware.com/agile/scrum/product-backlog
Theme | I want to… | So that… | Notes | Priority | Status | http://www.mountaingoatsoftware.com/uploads/blog/smaller-product-backlog.jpg
Fighter | 4 player format | Large groups can enjoy the game | 4 keys per each player | 2 | the game is only functional for 2 players at the moment and each player has 3 keys (up, left, and right)
Menu | Select player count and instructions | Players can choose how players and know how to play | 2-4 players and instructions | 8 | Menu offers tutorial and then when "Play" is clicked, player options apear. only 2 player possible so far
Start game | Go to the game stage | Players can get ready | Start up page | 7 | When button "2 players" is pressed, game starts and music plays
Map | Have platforms and barricades | Players don't die easily | Complex stage for strategy | 4 | Platforms and barriers all work. wall, floor, and ceiling all work.
Players | Have 4 different sprites | Players can distinguish themselves | Have separate sounds and color | 1 | There are currently only 2 characters and they do not make individual sounds
Player actions | Sprites auto fire and have the ability to move up and down and left and right | Players can move around | Sprites have 3 life. (accumulator = 3) | 3 | Sprites autofire and can move around. they have 5 lives
players die | explosion and disappears from stage | Players konw whos still alive | Make explosion custome | 5 | When players lives=0 they explode and other player says "I Won!!!"
Result | Show the remaining player as winner and congratulation background | Players know who won | Change background and wait 2 second til declaring winners | 6 | Background switches to confetti and winner is only sprite remaining